## Sheet1
Development Schedule
Week 1: Planning and Design | Week 2: Development Phase 1 | Week 3: Development Phase 2 | Week 4: Testing and Evaluation
create development schedule | create database that reflects the ERD and data dictionary | provide reports for each query | ensure all functions work as expected
outline purpose of software solution & provide detailed description of scenario | insert appropriate data into database | add function to allow multiple options to be added to order | adjust to repair any errors if found
provide ethical/legal/security issues that are relevant to software solution | check validity of data | add function to allow for delivery fee to be added on each order | provide evaulaution on product, how the solution meets the requirements
describe relevant factors that will affect the quality of the data in the solution | create SQL queries that fulfils all requirements | implement any suitable extra features for improved interaction | include discussion of any possible improvements/bugs and/or limitations
create ER diagram for tables in database & provide relational notation | ^ | create graphical user interface | provide a retrospective of development process and future impacts.
create the data dictionary with overviews of entities & key identification | ^ | ^
check over previous work completed - ensure all requirements are fulfilled | ^ | ^